## Slide 1
FREE-FIRST BUILD PLAN • VERSION 1.0
PERSONAL AI
COMMAND CENTER
A practical roadmap for Gmail, YouTube research, task management,
approvals and Shopify development — starting with free tools.
BUILD → TEST → CONNECT
Principle: no paid tools until a real bottleneck proves they are needed.
01

## Slide 2
01 / NORTH STAR
What the Command Center should actually do
One home screen that turns information into reviewed, trackable work.
02
CAPTURE
Bring in useful signals: Gmail messages, YouTube tutorials, business tasks and Shopify development notes.
THINK
Summarize, extract steps, suggest tasks, identify unknowns and draft a test plan — with sources attached.
CONTROL
Show proposed actions, ask for approval, execute only permitted actions and keep an audit log.
THE RULE THAT MAKES IT TRUSTWORTHY
AI can recommend and prepare. The user approves external or irreversible actions. Every integration starts with the smallest permission that works.

## Slide 3
02 / TOOL STACK
Start with free or already-available tools
Free tiers and limits change; verify current terms before relying on a service.
03
LAYER
FREE-FIRST OPTION
COST REALITY
DECISION / LIMIT
Dashboard
Existing HTML + GitHub repository
$0 to start
Keep the current prototype; track every change in version control.
Task database
SQLite locally; later Supabase Free or Google Sheets
$0 to start
Use one source of truth; export/backup from day one.
Automation
Manual triggers first; n8n Community self-hosted if suitable
Software can be free; hosting may not be
Self-hosting needs a computer/server that stays available and basic maintenance.
Gmail
Gmail API + Google OAuth
API standard use currently no extra charge
Read-only scope first; OAuth setup and consent configuration still required.
YouTube
YouTube Data API + available captions/transcripts
Quota / availability dependent
Video metadata is not the same as transcript access.
Shopify
Theme copy, local files, Shopify dev docs
No extra tool required to plan/test code
Never publish or change payments/domain without explicit approval.
Avoid subscriptions, paid AI APIs and always-on cloud hosting until the workflow is proven useful.

## Slide 4
03 / ARCHITECTURE
A simple architecture that can grow
Keep secrets off the frontend; separate the UI, data and external integrations.
04
DASHBOARD UI
HTML / JS
BACKEND API
Auth + validation
TASK DATABASE
SQLite → hosted DB
APPROVAL LOG
who / what / when
→
→
→
INTEGRATION ADAPTERS
Gmail (read-only) • YouTube research • Shopify theme tools • optional automation runner
Security boundary: API credentials and refresh tokens belong on the server, never in the HTML file or browser localStorage.

## Slide 5
04 / ROADMAP
Build in six small, testable phases
Do not integrate everything at once. Each phase must pass its exit test before the next begins.
05
WEEK 1
Stabilize prototype
Task add/edit/delete, unique IDs, schema validation, storage errors, export/import backup.
Exit: refresh, restart and restore tasks without data loss.
WEEK 2
Create task data layer
Define task schema, status states, due date, priority, source URL and activity log.
Exit: task data is consistent and exportable.
WEEK 3
Gmail read-only
Create Google Cloud project, enable Gmail API, OAuth consent, minimal read scope, fetch a few messages.
Exit: only approved messages/fields are read; no send/delete/modify.
WEEK 4
Approval engine
Proposed → approved → executed/failed; server validates approval; record action result.
Exit: rejected actions cannot execute; duplicate clicks do not duplicate work.
WEEK 5
YouTube research
Input URL, capture metadata, use transcript only when legitimately available, produce steps + tests.
Exit: output distinguishes video facts, assumptions and missing evidence.
WEEK 6+
Shopify safe development
Work on a theme copy, diff changes, preview and test; publish only after explicit approval.
Exit: rollback path exists and no live changes happen by default.

## Slide 6
05 / INTEGRATION 1
Gmail: read, summarize, suggest — never send
Start with one test account and the minimum scope. Google’s OAuth flow must be configured correctly.
06
1
Create a Google Cloud project
Enable Gmail API; configure consent screen and OAuth client.
2
Choose minimum permission
Use read-only scope for the first version; do not request send/modify access.
3
Fetch a small sample
List a few message IDs; retrieve only fields needed for task extraction.
4
Create task suggestions
Store subject, sender, date, short summary and message link; avoid copying full email bodies by default.
5
Human review
User confirms whether a suggestion becomes a task.
6
Test revocation + errors
Handle expired/revoked tokens, denied consent, quota errors and missing fields.
Official references: Gmail API Quickstart and OAuth 2.0 server-side authorization (links in final notes).

## Slide 7
06 / INTEGRATION 2
YouTube: turn a tutorial into an implementation playbook
Every video should produce a repeatable document, not just a summary.
07
INPUT
Video URL, creator/title, publication date, goal and your current stack.
EXTRACT
Metadata via API where available; transcript/captions only when available and permitted. Mark gaps clearly.
IMPLEMENT
Break into prerequisites, steps, commands, expected output, test, rollback and cost.
STANDARD OUTPUT TEMPLATE
Goal → prerequisites → exact steps → code/config → expected result → failure modes → security check → free-tier limits → acceptance test → next step
Important: a YouTube Data API response does not guarantee transcript access. If captions are missing, ask for a transcript or analyze the accessible description and state the limitation.

## Slide 8
07 / SAFETY BY DESIGN
Approval workflow is the system’s control plane
No external action should be executed just because a model suggested it.
08
DRAFT
AI proposes action
→
PENDING
Show exact changes
→
APPROVED
User explicitly approves
→
EXECUTING
Backend re-checks approval
→
DONE / FAILED
Record result + rollback
ALWAYS REQUIRE APPROVAL
Send email, publish theme, change payments/domain, delete data, spend money.
AUTOMATE LOW-RISK TASKS
Summaries, draft plans, local test runs, task suggestions.
LOG EVERY ACTION
Input source, proposed diff, approver, timestamp, result and failure reason.

## Slide 9
08 / DEFINITION OF DONE
Acceptance tests before calling it ‘automated’
A feature is complete only when success, failure and recovery are all tested.
09
DATA
Create/edit/delete tasks; export/import; restart browser; malformed storage recovers safely.
PERMISSIONS
Gmail connection is read-only; no send, delete, or modify API calls in Phase 1.
APPROVAL
Without an approval record, backend rejects the action. Duplicate requests are idempotent.
PRIVACY
Tokens are server-side; logs avoid full email contents and secrets.
YOUTUBE
Each step has source/time reference when available; unknowns are labeled, not invented.
SHOPIFY
Changes happen on a theme copy; preview and rollback are documented; publish is gated.
Track: status • evidence • blocker • next action • estimated cost • rollback tested?

## Slide 10
09 / START NOW
The first 48 hours: make progress without spending
Small deliverables first. No production accounts or live-store changes needed.
10
DAY 1 — BASELINE
Keep a backup of the current HTML. Create a private Git repository. Write down current features and known bugs.
DAY 1 — DATA CONTRACT
Define Task fields: id, title, status, priority, due_date, source_url, created_at, updated_at.
DAY 2 — HARDEN
Fix IDs, validation, storage errors, task edit/delete and export/import. Test refresh and restore.
DAY 2 — GMAIL PREP
Read the official quickstart; create a test project; plan a read-only OAuth scope. Do not paste secrets into chat or frontend code.
NEXT DELIVERABLE: a tested, backed-up dashboard before connecting any external account.

## Slide 11
APPENDIX / REFERENCES
Official documentation to follow
Tool pricing and free-tier limits can change; check before deployment.
11
Gmail API — Node.js quickstart
https://developers.google.com/workspace/gmail/api/quickstart/nodejs
Gmail API — OAuth server-side authorization
https://developers.google.com/workspace/gmail/api/auth/web-server
Gmail API — usage limits and quota notes
https://developers.google.com/workspace/gmail/api/reference/quota
Google OAuth 2.0 overview
https://developers.google.com/identity/protocols/oauth2
n8n — Google credentials / OAuth options
https://docs.n8n.io/integrations/builtin/credentials/google/
Google Cloud Free Tier details
https://docs.cloud.google.com/free/docs/free-cloud-features
Research note: Gmail API standard usage is currently listed as no additional cost, but quotas and billing terms can change. See official quota page.